## Activity
Dates | Comments
2015-12-20 | Paid 25k (first of three installments) to Prem by Anshul
2015-12-21 | Paid 41k to Lyk for A/C work by Anshul
2016-01-10 | Paid 5k token money to Raem kitchens by Sunny
2016-01-20 | Paid 5k to Virender for video door calling by Mom
2016-01-20 | Paid 5k token money to Spacewood kitchens by Sunny
2016-01-23 | Paid 50k to Spacewood kitchens by Sunny
2016-01-25 | Paid 20k advance for Aquavit WC + tanki and related equipments by Mom
2016-01-30 | Paid 5200 for Gas cylinder pipeline connection
2016-02-01 | Paid 50k to Ramjilal for advance for Plaster
2016-02-03 | Paid 23.4 k for frontier water tanks by Sunny
2016-02-09 | Paid 22k to Prem for tanki work by Anshul
2016-03-01 | Paid 1.5L to Ramjilal for internal plaster advance by Sunny
2016-03-14 | Paid 20k to Grill wala as advance
2016-03-18 | Paid 50k to ramjilal for advance for Plaster by Anshul
2016-03-20 | Paid 20k more to Grill waala
2016-03-28 | Paid 50k to Ramjilal for mumty by Sunny
2016-03-28 | Paid 25k as POP advance to Anand by Sunny
2016-04-09 | Paid 1.5L to Ramjilal for internal plaster 50k Anshul + 1L sunny
2016-03-14 | Paid 15k to Mushtaq for waterproofing for 5 bathrooms by Sunny
2016-03-15 | Paid 3k to Satish for pest control by Sunny
2016-04-10 | Paid 73.4k for wires purchase (electrical fittings) by Sunny - refer sheet electricals
2016-04-10 | Paid 72k to Spenza by Sunny- for details refer sheet bath and floor tiles
2016-04-10 | Paid 21.8k to Khandelwal by Anshul- for details refer sheet bath and floor tiles
2016-04-14 | Paid 25k as POP advance to Anand by Sunny
2016-04-25 | Paid 20k as POP advance to Anand by Sunny
2016-04-25 | Paid 15.5k plus 15.3k (Total 30.8k) for cement and dust respectively by Sunny
2016-05-03 | Paid 20k to Harjinder for Electrical labour charges by Sunny - refer sheet electricals
2016-05-03 | Paid 50k to Ramjilal for plaster by Sunny
2016-05-03 | Paid 25k to Mukesh for advance for tile fixing work by Sunny - refer sheet bath and floor tiles
2016-05-07 | Paid 5k as POP advance to Anand by Sunny
2016-05-12 | Paid 9k for wiring and pipes by Sunny - refer electricity sheet for bill wise details
2016-05-14 | Paid 17k to Spenza for White onex flooring tiles GF
2016-05-14 | Paid 11400 to Rainbow for Dyna flooring tiles GF
2016-05-14 | Paid 1k to Ceramica tiles, iffco for 2 pcs Satvario flooring tiles GF
2016-05-21 | Paid to Chain singh 25Kfor POP by Anshul
2016-05-16 | Paid 2.5k to chowkidar by Sunny
2016-05-23 | Paid 20k to Harjinder by Anshul
2016-05-25 | Paid 1.8k for water bill by Sunny
2016-05-31 | Paid 30k to Chain singh for PoP (25k by Anshul + 5k by Papa)
2016-06-07 | Paid 1 L to ramjilal by Anshul
2016-06-08 | Paid 6.5k to Mehan (chowkidaar) balance pymt for May by Sunny
2016-06-10 | Paid 12.2k to Pipes and tapes by Sunny for angle walls for bathrooms
2016-06-13 | Paid 10k to Mukesh for Tile work by Sunny
2016-06-21 | Paid 15.7k for cement (50 bags) by Sunny
2016-06-19 | Paid 30k to Mushtaq by Sunny for waterproofing
2016-06-19 | Paid 12.4k for electrical works by Sunny - refer electrical sheet for details
2016-06-22 | Paid 1.8k for rough POP (30 bags) by Sunny
2016-07-02 | Paid 10k to Swastik Marbles as advance by Sunny for Granite plus Italian
2016-07-03 | Paid 40k to Swastik Marbles as advance by Sunny for Granite plus Italian
2016-07-02 | Paid to Chain Singh (Till date - Rs. 1.90 lakhs paid to him) - details refer POP sheet
2016-07-03 | Paid 1.41k to Swastik Marbles as advance by Sunny for Granite plus Italian
2016-07-04 | Paid 10.5k to Mehan (chowkidaar) by Sunny
2016-07-08 | Paid 50k to Ramjilal by Sunny
2016-07-11 | Paid 70 k to Ramjilal by Anshul (including PCC of first floor)
2016-07-13 | Paid 7.5k for earthing with material by Sunny
2016-07-10 | Paid Rs 8k for Geyser of first floor by Anshul
2016-07-11 | Paid Rs 50k to Ramjilal by Sunny
2016-07-13 | Paid Rs 500 to Mehan chowkidar by Sunny
2016-07-14 | Paid Rs 2.9k for electric pipes (underground) by Sunny
2016-07-20 | Paid Rs 1.2k for water bill by Sunny
2016-07-22 | Paid Rs 4.4k for ground floor flooring by Sunny
2016-07-22 | Paid Rs 5k to chain singh and Rs 10k to Amit by Anshul
2016-07-22 | Paid Rs 1.2k for LED lights Syska and Pix by Sunny
2016-07-24 | Paid Rs 500 to Mehan chowkidar by Sunny
2016-07-25 | Paid Rs 1.2 k for Phillips LED lights by Sunny
2016-07-26 | Paid 3k to Mukesh and 1k to Satish by Sunny
2016-07-28 | Paid Rs 0.6k for waterproofing material by Sunny
2016-07-30 | Paid Rs 1.8k for LED lights Phillips from Iffco chowk by Sunny
2016-07-31 | Paid Rs 1k for Phillips LED light by Sunny
2016-08-01 | Paid Rs 2.3k commercial tiles by Sunny
2016-08-02 | Paid Rs 0.8k for Syska LED light by Sunny
2016-08-03 | Paid Rs 30k to chain singh by Anshul
2016-08-03 | Paid Rs 0.5k for waterproofing material by Sunny
2016-08-03 | Paid Rs 15.5k for Dust by Sunny
2016-08-04 | Paid Rs 40k to Mukesh by Anshul
2016-08-06 | Paid Rs 1.6k Philiips 15w by Sunny
2016-08-09 | Paid 9k for Paint material by Anshul |  |  | 100 | gudmala
2016-08-14 | Paid Rs 4.3k for Motor and Rs 4k for commercial tiles and 0.5k for electrical items by Sunny |  |  | 120 | grout
2016-08-16 | Paid Rs 15.75k for cement by Anshul |  |  | 80 | bulb holder
2016-08-16 | Paid to Adhunik Marbles Rs 37500 for Granite by Sunny for GF front and back |  |  | 200 | 20 mtr wire
2016-08-17 | Paid to Mukesh Rs 10k by Anshul |  |  | 500
2016-08-20 | Paid Rs 2.7k for commercial tiles by Sunny
2016-08-21 | Paid Rs 2.9k to Khandelwal tiles (6boxes) for FF by Anshul
2016-08-23 | Paid Rs 0.3k white cement and black grout for GF bathroom by Sunny
2016-08-27 | Paid Rs 12k to Chain singh by Anshul
2016-09-02 | Paid Rs 15k to Amit by Sunny
2016-09-04 | Paid Rs 50k to Mukesh by Anshul
2016-09-04 | Paid Rs 5k to Chain singh by Sunny
2016-09-05 | Paid Rs 25k to Mukesh and 9k to Mehan by Sunny
2016-09-07 | Paid Rs 50k to Ramjilal by Anshul
2016-09-10 | Paid Rs 10k to Chain singh by Sunny
2016-09-11 | Paid 12k for FF kitchen tiles and 8 pieces from khandelwal for 0.4k by Anshul
2016-09-14 | Paid Rs 26.5k from bath selection for FF balcony tiles by Anshul
2016-09-14 | Paid Rs 21.7k for electricity bill by Sunny
2016-09-15 | Paid Rs 1.5k for Regmark by Sunny
2016-09-16 | Paid Rs 7.2k for GF kids BR wooden tiles by Sunny
2016-09-16 | Paid Rs 54k for Flush door to Mittal by Sunny
2016-09-17 | Paid Rs 16.3k for Mica by Anshul for Moms doors
2016-09-18 | Paid Rs 19k for paint items by Sunny | 18915
2016-09-25 | Paid Rs 0.6k for paint items by Sunny
2016-09-27 | Paid Rs 26k (12k Anshul + 14k Sunny) for Granite paid respectively
2016-09-27 | Paid Rs 6.5k for paint and door items by |  | 4900 |  | 1242
2016-09-29 | Paid Rs 2.3k for electricity and water bill by Sunny |  | 1600 |  | 1124
2016-09-29 | Paid Rs 5.5k for FF kitchen tiles by Bath selection by Anshul |  | 6500 |  | 2366
2016-10-02 | Paid Rs 11.8k for paint items by Anshul
2016-10-04 | Paid Rs 1.08k by Anshul and 1.08 by Sunny for HUDA FAR increase
2016-10-04 | Paid Rs 5k to Mehan by Sunny and 4k by Anshul
2016-10-07 | Paid Rs 20k to HUDA outstanding arrears to HUDA by Sunny
Note on C22: Sumit Malik: balance 6k to be paid on final work

## Ramjilal
Payments made to Ramjilal (Contractor)
Phase | Installment | Date of payment | Amount | Cummulative | Status | Paid by
0 | Mobilisation advance | 2014-12-10 | 20000 | 300000 | Paid
| Mobilisation advance | 2014-12-16 | 100000 |  | Paid
| Mobilisation advance | 2015-03-22 | 180000 |  | Paid
1 | Paid to Shyam stones | 2015-04-20 | 36800 | 482800 | Paid
| At DPC level1 | 2015-04-20 | 300000 |  | Paid |  |  | 266028.75 | -61971.25
| At DPC level2 | 2015-05-28 | 120000 |  | Paid |  | Total | 10% total | 10% after adjusting mobilization adv | 15% total | 15% after adjusting mobilization adv
| Pending | 2015-05-28 | 26000 |  | Paid |  | 3547050 | 354705 | 304705 | 532057.5 | 482057.5
2 | Ground floor slab advance | 2015-06-11 | 200000 | 482000 | Paid
| Ground floor slab | 2015-06-17 | 100000 |  | Paid
| Ground floor slab - pending | 2015-06-22 | 182000 |  | Paid | sunny/anshul
3 | First floor slab advance | 2015-07-14 | 100000 | 482000 | Paid | Sunny
| First floor slab | 2015-07-16 | 382000 |  | Paid | Sunny
[5 empty] | Paid | Sunny
4 | Brickwork advance 1 | 2015-07-07 | 25000 | 304000 | Paid | Sunny
| Brickwork advance 2 | 2015-07-08 | 25000 |  | Paid | Sunny
| Brickwork advance 3 | 2015-07-13 | 40000 |  | Paid | Sunny
| Brickwork | 2015-09-10 | 100000 |  | Paid | Anshul
| Wood advance (Anshul) | 2015-10-18 | 50000 |  | Paid | Anshul
| Wood advance (sunny) | 2015-10-18 | 54000 |  | Paid | Sunny
| Final payment | 2015-12-07 | 10000 |  | Paid | Sunny
5 | Second floor slab | 2015-08-13 | 300000 | 482000 | Paid | Anshul
| Second floor slab - pending | 2015-08-21 | 182000 |  | Paid | Anshul
6 | Watertank + mumty + mumty balcony | 2015-10-28 | 250000 | 250000 | Paid | Sunny
7 | Internal Plaster (advance) | 2015-12-07 | 40000 | 304000 | Paid | Sunny
| Internal Plaster (advance 2) | 2016-02-01 | 50000 |  | Paid | Anshul
| Internal Plaster | 2016-03-01 | 150000 |  | Paid | Sunny
| Internal Plaster | 2016-03-18 | 50000 |  | Paid | Anshul
| Internal Plaster | 2016-04-09 | 14000 |  | Paid | Anshul
8 | Outer Plaster - 1 | 2016-04-09 | 36000 | 328000 | Paid | Anshul
| Outer Plaster - 2 | 2016-04-09 | 100000 |  | Paid | Sunny
| Outer Plaster - 3 | 2016-05-03 | 50000 |  | Paid | Sunny
| Outer Plaster - 4 | 2016-06-07 | 100000 |  | Paid | Anshul
| Outer Plaster - 5 | 2016-07-08 | 42000 |  | Paid | Sunny
9 | Open area construction - 1 | 2016-07-08 | 8000 | 128000 | Paid | Sunny
| Open area construction - 2 | 2016-07-11 | 50000 |  | Paid | Anshul
| Open area construction - 3 | 2016-07-11 | 50000 |  | Paid | Sunny
| PCC for first floor (to be borne by Anshul) | 2016-07-11 | 20000 |  | Paid | Anshul
Total |  |  | 3542800 | 3542800
On Dec7 Ramjilal asked for 50k, out of which
10k completes brick work payment and 40k
becomes advance for internal plaster stage.
On April 9 Ramjilal asked for 1.50L, out of which
14k completes Internal plaster payment and 1.36
becomes advance for outer plaster stage.
Note on H14: Sumit Malik: Need to check this
Note on D40: Sumit Malik: actually paid on 9 feb 16 missed earlier.
Note on E41: Sumit Malik: sq fr 650 * 35 = 22750 actually payable adjusted with cement money to be recovered of 3250..balance 500 also to be adjusted from his later payment

## Payment by
Details of money paid by Anshul/ Sunny as on 13 July 16
PAID BY
| Mummy | Anshul | Sunny
Ramjilal | 1082800 | 1023000 | 1367000
Sanitary fittings | 0 | 10000 | 64270
Tiles |  |  | 115274
Electrician |  | 20000 | 114744
POP |  | 75000 | 115000
A/c |  | 41500 | 0
Kitchen |  | 0 | 60000
Prem Plumber |  | 47000 | 0
Chowkidaar |  | 0 | 19500
Granite |  | 0 | 76300
Waterproofing, watertanks, pest control, earthing & Misc |  | 0 | 108600
Grand Total |  | 1216500 | 2040688
Excess paid by Sunny |  |  | 824188

## Amit
Payments made to Amit (Architect)
Phase | Installment | Date of payment | Amount | Status | Paid By
0 | Advance money | 2014-07-28 | 10000 | Paid
1 | At submission stage | 2014-11-05 | 15000 | Paid
2 | At DPC stage | 2015-04-06 | 30000 | Paid
3 | For ground floor slab | 2015-07-03 | 10000 | Paid
4 | For first floor slab | 2015-07-19 | 20000 | Paid | Sunny
5 | For second floor slab | 2015-08-21 | 20000 | Paid | Anshul
Total |  |  | 105000
1082000
55000
144500
23000
1304500

## HUDA
Payments made to HUDA (legally)
Phase | Installment | Date of payment | Amount | Status
0 | For increased Area | 2014-07-28 | 120000 | Paid
1 | Water | 2014-11-05 | 5500 | Paid
2 | Electricity | 2014-11-05 | 17000 | Paid
3 | DPC | 2015-04-06 | 2000 | Paid
Total |  |  | 144500

## Others
Payments made to Others (Illegally)
Phase | Installment | Date of payment | Amount | Status
0 | At Plan Submission | 2014-07-28 | 15000 | Paid
1 | Demarcation | 2014-11-05 | 4000 | Paid
2 | DPC | 2015-04-06 | 4000 | Paid
Total |  |  | 23000

## Kharcha
Round-off
Total loan | 4000000
Mom's part in loan | 1000000
Mom: Already given for plot buying | 200000
Mom: Contribution reserved for construction | 800000
Mom: Pending to Anshul | 100000
Mom's contribution till now for construction | 1082000 | Ramjilal
| 30000 | Amit
| 22500 | Water+Electricity
| 120000 | Huda (Revised area)
| 6000 | DPC (2k illegal to Architect + 4k Illegal to HUDA)
| 4000 | Demarcation (illegal given to amit)
1264500
Extra paid by Mom | 464500 |  | 4,60
Sunny needs to pay | 232250 |  | 2,30
Anshul needs to pay | 232250 |  | 2,30
But mom had to pay me 1Lakh, so effective | 132250 |  | 1,30
My share for ground floor slab pending payment to Ramjilal | 182000/2 |  | 91
So my total outstanding as on 22 June 2015 |  |  | 221

## Wood
Wood Expenses for Chaukhat (bought on 18 Oct 2015)
Summary
Wood type | Sudan Teak | Phase 2 | Dec 7 2015
Price (Rs per foot) | 1730 | Quantity (in foot) | 11.72
Quantity (in foot) | 81.46 | Total | 20275.6
Total | 140925.8 | Paid by Ramjilal | 15001.6
Paid by Ramjilal | 104268.8 | Paid by us | 5274
Paid by us | 36657
Details of payment
As per agreement ramjilal had to pay for Chaap
Price for chaap | 1280
Quanity | 81.46
Total for chaap | 104268.8
Details for wood size
7 foot pieces | 3
8 foot pieces | 64
9 foot pieces | 26
Total | 93

## Plumber
Prem Plumber
2015-12-20 | Paid 25k (first of three installments) to Prem by Anshul
2016-02-09 | Paid 22k to Prem for tanki work by Anshul

## Bathroom
Ground Floor (Sunny)
Item | Brand | Purpose | Price/piece | Quantity | Total Cost | Bought on | Paid by
WC | Jaguar | In bathroom | 10870 | 1 | 10870 |  | Sunny
Cistern | Kohler | Out bathroom | 4000 | 1 | 4000 |  | Sunny
Cistern | Grohe | In bathroom | 5200 | 1 | 5200 |  | Sunny
Diverter (inner part) | Jaguar | In bathroom | 2900 | 1 | 2900 |  | Sunny
Diverter (inner part) | Kohler | Out bathroom | 3240 | 1 | 3240 |  | Sunny | Total | 74270
Mutha Bracket |  | Both | 300 | 2 | 600 |  | Sunny | Paid By | Amount
[5 empty] | 26810 |  |  | Anshul | 10000
[8 empty] | Mom | 11290
First Floor (Anshul) | [7 empty] | Sunny | 52980
Item | Brand | Purpose | Price/piece | Quantity | Total Cost | Bought on | Paid by |  | 74270
WC | Jaguar | In bathroom | 8990 | 1 | 8990 |  | Sunny
WC | Aquavit | Out bathroom | 8300 | 1 | 8300 |  | Sunny
Cistern | Kohler | Out bathroom | 4000 | 1 | 4000 |  | Sunny
Cistern | Grohe | In bathroom | 4650 | 1 | 4650 |  | Sunny
Diverter (inner part) | Jaguar | In bathroom | 2900 | 1 | 2900 |  | Sunny
Diverter (inner part) | Kohler | Out bathroom | 3240 | 1 | 3240 |  | Sunny
Basin mix Diverter (inner part) | Jaguar | Out bathroom | 2280 | 1 | 2280 |  | Sunny
Mutha Bracket |  | Both | 300 | 2 | 600 |  | Sunny
34960
Second Floor (Mom)
Item | Brand | Purpose | Price/piece | Quantity | Total Cost | Bought on | Paid by
Diverter (inner part) | Jaguar | Out bathroom | 2900 | 1 | 2900 |  | Sunny
Cistern | Kohler | Out bathroom | 4650 | 1 | 4650 |  | Sunny
Cistern | Grohe | In bathroom | 4650 | 1 | 4650 |  | Sunny
Mutha Bracket |  | Out bathroom | 300 | 1 | 300 |  | Sunny
12500
Angle walls and other misc items purchased etc
16 angle wall |  | 4480
3 angle wall jaguar |  | 3540
1 angle wall local |  | 750
10 extn nip 1 inch |  | 700
25 extn nip 1.5 inch |  | 1200
6 extn nip 2 inch |  | 540
6 extn nip 2.5 inch |  | 660
17 cpc caps |  | 340
|  | 12210 | Total paid by Sunny
Anshul share |  | 5000
Sunny share |  | 7200

## AC
A/C work done by Lyk on Dec 19 and 20
Quotation |  |  |  |  | Price in Rs
Item | Brand | Size |  |  | 550/meter | if outlet copper pipe is 12mm
Copper pipe | Malaysia | 1.5 ton | outlet - 12 mm |  | 580/meter | if outlet copper pipe is 15 mm
|  |  | inlet - 6 mm |  | 80/meter | for drain pipe
|  | 2 ton | outlet - 15 mm
inlet - 6 mm
Its Insulation
Power cable | National | 4 core
Drain pipe | PVC | 25 mm
Its Insulation |  | 3 mm
Actual Price
Item | Price/meter | Quantity in meters | Charges | Charges Per floor
Drain pipe | 80 | 40.24 | 3219.2
Everything else
Ground floor | 550 | 26.8 | 14740
First floor | 580 | 15.5 | 8990 | 14820
| 550 | 10.6 | 5830
Second floor | 580 | 10.8 | 6264 | 8739
| 550 | 4.5 | 2475
Total |  |  | 41518.2

## Grill
Grill work done by Bittoo on March 20
Actual Price
Item | Price/foot | Running length (in feet) | Height (in feet) | Total feets | Total price | Total price after discount
Ground Floor | 140 | 55 | 3 | 165 | 23100 | 21714 | Sunny | 14440.75
First floor | 140 | 24.5 | 2.5 | 61.25 | 8575 | 8060.5 | Anshul | 28094.25
Second floor | 140 | 24.5 | 2.5 | 61.25 | 8575 | 8060.5 | Total | 42535
Gate (Mumty) | 4500 | 1 | 1 | 1 | 4500 | 4230
Lock (in gate) | 500 | 1 | 1 | 1 | 500 | 470
Total |  |  |  |  | 45250 | 42535

## Video door calling
Video Door Calling work done by Veerender on 20th Jan 2016
Quotation
Items | Type | Subtype | Brand | Cost
Unit | Outdoor unit |  | CP Plus
| Indoor unit | screen 4 inch | CP Plus | 27000
|  | screen 7 inch | CP Plus | 30000
| Lock + power supply |  | CP Plus
Cable | Cat6 |  | Dlink | 20 Rs per foot
Labour | Jhiri katna |  |  | 90 Rs per meter
Actual
Items | Type | Subtype | Brand | Length | Cost
Unit | Outdoor unit |  | CP Plus
| Indoor unit |  | CP Plus
|  | screen 7 inch | CP Plus |  | 30000
| Lock + power supply |  | CP Plus
Cable | Cat6 |  | Dlink | 70 feet | 1400
Labour |  |  |  | 25 | 2250
|  | Total |  |  | 33650
|  |  |  | Discount | 150
|  |  |  | Final | 33500

## Kitchen
Kitchens
2016-01-10 | Paid 5k token money to Raem kitchens by Sunny
2016-01-20 | Paid 5k token money to Spacewood kitchens by Sunny
2016-01-23 | Paid 50k to Spacewood kitchens by Sunny

## Cylinder
Cyliner fitting work done by Shoufeeq Khan on 30th Jan 2016
Quotation
Items | Price per feet | Quantity | Total Cost
Copper Pipe | 160 | 30 feet | 4800
Nozzle | 200 | 4 | 800
Labour | 400 | 2 | 800
6400
Actual
Items | Price per feet | Quantity | Total Cost
Copper Pipe | 160 | 21.5 feet | 3440
Nozzle | 200 | 4 | 800
Labour | 400 | 2 | 800
|  | Total | 5040
|  | Inaam | 160
|  | Final Total | 5200

## Bath & floor Tiles
Bathroom and floor tiles
Actual paid
[8 empty] | First Floor | [5 empty] | Second Floor
Ground Floor |  | Type | Shop | Rate per sq ft | Total Sq fts | Total |  | Type | Shop | Rate per sq ft | Total Sq fts | Total |  | Type | Rate per sq ft | Total Sq fts | Total | Shop
Bathroom (of master BR)
Base wall Tile |  | Pearl white | Spenza | 39 | 210 | 8190 |  | Onax beige | Spenza | 46 | 200 | 9200 | [6 empty] | 46 | 208
Highlighter |  | White and black | Spenza | 180 | 27 | 4860 |  | Brown | Khandelwal
Floor |  | Slate neo |  | 38 | 45 | 1710 |  |  |  |  | Total | 9200
[5 empty] | Total | 14760 |  |  |  |  | with tax | 9798
[5 empty] | with tax | 15719.4 | 16269.4
Bathroom (common)
Base wall Tile |  | Sandy Grey dark | Spenza | 46 | 180 | 8280 |  | White | Khandelwal | 52 | 210 | 10920 |  | Onax beige | 46 | 208 | 9568 | Spenza
Highlighter |  | Silver mosaic | Spenza | 320 | 18 | 5760 |  | Black and silver | Khandelwal | 320 | 24 | 7680 |  | Golden quatro | 120 | 27.5 | 3300 | MLS
Floor | [9 empty] | 48 | 40 | 1920 |  | Braccia brn | 38 | 45 | 1710 | Spenza
[5 empty] | Total | 14040 |  |  |  |  | Total | 20520 |  |  |  |  | 14578
Kitchen |  |  |  |  | with tax | 14952.6 |  |  |  |  | With tax | 21800 |  |  |  | With tax | 15525.57
Highlighter |  | Designer | Spenza | 900 | 16 | 14400
[5 empty] | with tax | 15336
2016-05-03 | Paid 25k to Mukesh for advance for tile fixing work
2016-04-25 | Paid 15.5k plus 15.3k (Total 30.8k) for cement and dust respectively for own purchase
2016-06-13 | Paid 10k to Mukesh for Tile work by Sunny
|  |  |  | Total paid to Spenza as per above |  |  | 71881.57 | Spenza
|  |  |  | Total paid to khandelwal as per above |  |  | 21800 | Khandelwal
93681.57
Supporting
[6 empty] | Spenza bill | 29284 | copy on maliks
[6 empty] | Spenza bill | 23600 | copy on maliks
[6 empty] | Spenza bill | 3840 | copy on maliks
[6 empty] | Spenza bill | 12200 | copy on maliks
[6 empty] | Khand bill | 21800 | copy on maliks
[6 empty] | Total | 90724
[6 empty] | Diff | 2957.57
Bedrooms
|  | White onex | [5 empty] | Marble - Buttachino Crema | Galaxy, Chattarpur | 295 | 446.4407 | 131700 |  | Onax beige | 46 | 169 | 7774 | Spenza
|  | dyna | Rainbow | 80 | 263.075 | 21046 | [7 empty] | White onex | 91.42 | 170.64 | 16973.9088 | Spenza
|  | satvario | Ceramics Iffco | 73 | 222.4658 | 16240
37286
|  | De martino | Swastik | 250 | 457.47 | 117067.5 |  | Granite (common) | Swastik | 110 | 660 | 76300 | paid by Sunny
Paid by Sunny
Note on H11: Sumit Malik: With moulding of Rs 550

## Electrical
Electrical fittings and Labour
Electrical items
Wires
Bill date | Amount
2016-06-25 | 630
2016-06-10 | 1440
2016-05-01 | 1810
2016-05-05 | 4550
2016-05-10 | 940
2016-06-10 | 35600
2016-04-24 | 5330
2016-05-01 | 6324
2016-05-01 | 880
2016-05-07 | 5900
2016-05-22 | 2300
2016-05-22 | 150
2016-05-22 | 130
2016-06-10 | 26880
2016-06-10 | 630
2016-06-10 | 1250
| 94744 | All paid by Sunny
Total entries in activity sheet for the above expenses
| 73370 | Sunny
| 8953 | Sunny
| 12421 | Sunny
Total | 94744
Earthing
Material | 4500
Labour | 3000
Total | 7500

## POP
POP and false ceiling
|  |  | 75k | anshul
Agreement with Anand/ Chain singh with material |  |  | 115k | Sunny
Date | Description | Paid by
2016-03-28 | Paid 25k as POP advance to Anand | Sunny
2016-04-14 | Paid 25k as POP advance to Anand | Sunny
2016-04-25 | Paid 20k as POP advance to Anand | Sunny
2016-05-07 | Paid 5k as POP advance to Anand | Sunny
2016-05-21 | Paid 25k as POP advance to Anand | Anshul
2016-05-31 | Paid 30k to Chain singh for PoP (25k by Anshul + 5k by Papa) | Anshul
2016-06-20 | Paid 30k as POP advance to Anand | Sunny
2016-07-02 | Paid 20k as POP advance to Anand | Anshul
2016-07-02 | Paid 10k as POP advance to Anand | Sunny